## Sheet1
Time | 3.24 | 3.25-4.14 | 4.15-4.23 | 4.24-4.25 | 4.26 | 4.27 | 4.28
Stage | Pre-production | Production01 - Alpha Build | Production02 | Play Test | Polish | Play Test2 and Polish2 | End of Project
Rough tasks | Pitch, Asset List, GDD | 3C's, Asset | UI, Asset, Tutorial | All fuction | Fix bug | Debug | Show
Completion (update)
Production01 - Alpha Build

## Programer Scheduling
Production01 - Alpha Build
3.30~4.6 | 4.7~4.10 |  |  |  | 4.11~4.12 |  | 4.13
Scenes | Tower |  |  |  | Enemy |  | Alpha Build | program
Map Tool | Build Tower | Upgrade Tower | Sell Tower | Tower Function | AI |  | Alpha Build
3.29 | 3.30~4.1 |  |  |  |  | 4.2~4.5 | [6 empty] | 4.6~4.12
3C Design | Scene |  | Tower Design |  | Level | Slingshot Ball |  |  | Enemy |  |  | UX | Level | Animation | design
Control Design | Scene Asset |  | Tower Variety | Value Variety | Layout | Sling Tower Ball | Sling Upgrade Ball | Sling Sell Ball(?) | AI | Value Variety | Enemy Variety | UX Function | Level build | Animation
3.31
Slingshot |  |  |  | Oprah, Matt
Base Sling | Sling Tower | Sling Upgrade | Sling Sell
3.31 | 4.1~4.5 |  |  |  | 4.6~4.7
Artstyle | Slingshot |  |  |  | Scene |  | Tower Design |  | Enemy |  | UI
Artstyle | Base Sling | Sling Tower | Sling Upgrade | Sling Sell | Scene Asset |  | Tower Variety | Value Variety | Value Variety | Enemy Variety | UI art

## Tower
dps | Tower Name | Cost | Sell | Range (radius, grid) | Damage (/projectile) | Attack Interval (sec) | Attack Speed (/sec) | Projectile Speed (gird/sec) | Details
15 | Basic Lv.1 | 60 | 42 | 3 grid | 5 | 0.33333 | 3 | 10 | Single body attack, no sputtering
32 | Basic Lv.2 | 60 | 42 | 3.5 grid | 8 | 0.25 | 4 | 15
50 | Basic Lv.3 | 60 | 42 | 4 grid | 10 | 0.2 | 5 | 20
max dps | Tower Name | Cost | Sell | Range (radius, grid) | Damage (/projectile) | Attack Interval (sec) | Attack Speed (/sec) | Lightning Damage Transmitted | Ligtning Length (Enemy Number) |  | Details
36 | Tesla Lv.1 | 120 | 84 | 5 grid | 6 | 0.25 | 4 | 50% | 2 |  | Projectile no delay, Lightning damage can be transmitted
76.65 | Tesla Lv.2 | 120 | 84 | 6 grid | 7 | 0.2 | 5 | 70% | 3
121.584 | Tesla Lv.3 | 120 | 84 | 7 grid | 8 | 0.16667 | 6 | 70% | 4
max dps | Tower Name | Cost | Sell | Range (radius, grid) | Damage (/projectile) | Attack Interval (sec) | Attack Speed (/sec) | Projectile Speed (gird/sec) | Details
32 | Double-end Lv.1 | 70 | 49 | 3 grid | 16 | 0.5 | 2 | 14 | Single body attack, no sputtering, Simultaneous emission in both directions
72 | Double-end Lv.2 | 70 | 49 | 4 grid | 24 | 0.33333 | 3 | 15
100 | Double-end Lv.3 | 70 | 49 | 5 grid | 25 | 0.25 | 4 | 16
dps | Tower Name | Cost | Sell | Range (radius, grid) | Damage (/projectile) | Attack Interval (sec) | Attack Speed (/sec) | Projectile Speed (gird/sec) | Explosion Range (radius, grid) |  | Details
20 | Missile Lv.1 | 140 | 98 | 8 grid | 20 | 1 | 1 | 3 | 0.3 |  | Projectile AOE
30 | Missile Lv.2 | 140 | 98 | 9 grid | 25 | 0.83333 | 1.2 | 4 | 0.4
40 | Missile Lv.3 | 140 | 98 | 10 grid | 32 | 0.8 | 1.25 | 5 | 0.5
dps | Tower Name | Cost | Sell | Range (radius, grid) | Burning Damage (/sec) | Burning Time (/sec) | Burning Range (radius, grid) | Details
30 | Flame-thrower Lv.1 | 130 | 91 | 1.5 grid | 6 | 4 | 0.2 | AOE, no delay, continuous damage Conflicts with deceleration effect
40 | Flame-thrower Lv.2 | 130 | 91 | 2 grid | 8 | 5 | 0.25
50 | Flame-thrower Lv.3 | 130 | 91 | 2 grid | 10 | 5 | 0.3
dps | Tower Name | Cost | Sell | Range (radius, grid) | Attack Speed (/sec) | Attack Interval (sec) | Stun Chance | Stun Duration (sec) | Details
/ | Blast Lv.1 | 50 | 35 | 1 grid | 0.3 | 3.3333 | 40% | 0.3 | AOE no harm, Stun the enemy
/ | Blast Lv.2 | 50 | 35 | 1.25 grid | 0.4 | 2.5 | 50% | 0.4
/ | Blast Lv.3 | 50 | 35 | 1.5 grid | 0.5 | 2 | 60% | 0.5
average dps | Tower Name | Cost | Sell | Range (radius, grid) | Damage (/projectile) | Attack Interval (sec) | Attack Speed (/sec) | Projectile Speed (gird/sec) | Critical Chance | Critical Multiplier | Details
24 | Crossbow Lv.1 | 80 | 56 | 8 grid | 40 | 2 | 0.5 | 15 | 20% | 200% | Single body attack, no sputtering, Crtical damage
48.75 | Crossbow Lv.2 | 80 | 56 | 9 grid | 50 | 1.3333 | 0.75 | 20 | 30% | 200%
78 | Crossbow Lv.3 | 80 | 56 | 10 grid | 60 | 1 | 1 | 25 | 30% | 200%
https://assetstore.unity.com/packages/3d/characters/simple-tower-defense-kit-105986

## Enemy
Name | Life | Speed (grid/sec) | Reward | Heart Loss | Details | Old
Regular | 60 | 0.5 | 6 | 1 | /
Strong | 150 | 0.4 | 10 | 1 | /
Fast | 30 | 0.8 | 3 | 1 | /
Boss | 1500 | 0.3 | / | ∞ | Once killed, win the level
Name | Life | Speed (grid/sec) | Reward | Heart Loss | Details | New
Regular | 50 | 0.5 | 5 | 1 | /
Strong | 200 | 0.4 | 10 | 1 | /
Fast | 15 | 1 | 1 | 1 | /
Giant | 1500 | 0.3 | 20 | 5 | /

## New Level
Initial Gold: 60 |  |  | Initial Life: 20 |  | Gold Growth: 1/sec
Round | True Interval | Name | Speed (grid/sec) | Number | Distance(gird) | gap time (sec) | Spawn Time | *Last Time (sec) | Rewards | Money at begin
1 | 40 | Regular | 0.5 | 5 | 0.8 | 1.6 | 0 | 8 | 25 | 90
2 | 40 | Fast | 0.8 | 10 | 0.8 | 1 | 0 | 10 | 10 | 155
3 | 40 | Strong | 0.4 | 3 | 2 | 5 | 0 | 15 | 30 | 205
4 | 40 | Regular | 0.5 | 10 | 0.75 | 1.5 | 0 | 15 | 50 | 275
|  | Giant | 0.3 | 1 |  | 0 | 15 | 0
Initial Gold: 100 |  |  | Initial Life: 20 |  | Gold Growth: 1/sec
Round | True Interval | Name | Speed (grid/sec) | Number | Distance(gird) | gap time (sec) | Spawn Time | *Last Time (sec) | Rewards | Money at begin
1 | 20 | Regular | 0.5 | 10 | 0.8 | 1.6 | 0 | 16 | 50 | 100
2 | 40 | Fast | 0.8 | 30 | 0.8 | 1 | 0 | 30 | 30 | 190
3 | 40 | Giant | 0.3 | 1 | 0 | 0 | 0 | 0 | 20 | 260
|  | Regular | 0.5 | 30 | 0.6 | 1.2 | 14 | 36 | 150
4 | 60 | Strong | 0.4 | 20 | 1 | 2.5 | 0 | 50 | 200 | 490
5 | 60 | Strong | 0.4 | 40 | 0.5 | 1.25 | 0 | 50 | 400 | 750
|  | Giant | 0.3 | 5 | 4.2 | 14 | 0 | 70 | 100
Initial Gold: 0 |  |  | Initial Life: 6 |  | Gold Growth: 2/sec
Round | True Interval | Name | Speed (grid/sec) | Number | Distance(gird) | gap time (sec) | Spawn Time | *Last Time (sec) | Rewards | Money at begin
1 | 10 | Strong | 0.4 | 2 | 6 | 15 | 0 | 30 | 20 | 20
2 | 25 | Fast | 0.8 | 50 | 0.4 | 0.5 | 0 | 25 | 50 | 90
3 | 25 | Giant | 0.3 | 1 | 0 | 0 | 0 | 0 | 20 | 190
4 | 60 | Strong | 0.4 | 10 | 0.8 | 2 | 0 | 20 | 100 | 330
5 | 30 | Giant | 0.3 | 1 | 0 | 0 | 0 | 0 | 20 | 490
|  | Giant | 0.3 | 2 | 0.6 | 2 | 5 | 4 | 40
Initial Gold: 400 |  |  | Initial Life: 1 |  | Gold Growth: 1/sec
Round | True Interval | Name | Speed (grid/sec) | Number | Distance(gird) | gap time (sec) | Spawn Time | *Last Time (sec) | Rewards | Money at begin
1 | 20 | Giant | 0.3 | 5 | 1.5 | 5 | 0 | 25 | 100 | 410
2 | 60 | Fast | 0.8 | 100 | 0.2 | 0.25 | 0 | 25 | 100 | 540
3 | 60 | Giant | 0.3 | 10 | 2.1 | 7 | 0 | 70 | 200 | 670
|  | Fast | 0.8 | 100 | 0.4 | 0.5 | 0 | 50 | 100

## Old Level
Initial Gold: 40 |  |  |  | Initial Life: 20
Round | True Interval | Interval (sec) | Interval Begin Time | Name | Speed (grid/sec) | Number | Density (/gird) | gap distance(grid) | gap time (sec) | Spawn Time | Last Time (sec) | Total Gold
1 | 30 | 30 | 0:10 | Regular | 0.5 | 5 | 1 | 1 | 2 | 0:00 | 10 | 25 | 110 | 257
2 | 40 | 30 | 0:45 | Strong | 0.4 | 6 | 1 | 1 | 2.5 | 0:00 | 15 | 55
3 | 75 | 30 | 0:40 | Fast | 0.8 | 10 | 1.5 | 0.66667 | 0.83333 | 0:00 | 8.3333 | 20 | 147
4 | 90 | 30 | / | Fast | 0.8 | 15 | 2.5 | 0.4 | 0.5 | 0:06 | 7.5 | 75
|  |  |  | Boss | 0.3 | 1 | / |  |  | 0:15
*Interval begins counting down when all enemies have spawned in a round
Initial Gold: 400 |  |  |  | Initial Life: 20
Round | True Interval | Interval (sec) | Interval Begin Time | Name | Speed (grid/sec) | Number | Density (/gird) | gap distance(grid) | gap time (sec) | Spawn Time | Last Time (sec) | Total Gold
1 | 30 | 30 | 0:30 | Regular | 0.5 | 12 | 1 | 1 | 2 | 0:00 | 24 | 60 | 90 | 402
|  |  |  | Regular | 0.5 | 6 | 2 | 0.5 | 1 | 0:30 | 6 | 30
2 | 60 | 30 | 0:20 | Strong | 0.4 | 8 | 0.5 | 2 | 5 | 0:00 | 40 | 72 | 202
|  |  |  | Fast | 0.8 | 20 | 2.5 | 0.4 | 0.5 | 0:20 | 10 | 40
|  |  |  | Strong | 0.4 | 10 | 1 | 1 | 2.5 | 0:50 | 25 | 90
3 | 50 | 30 | 0:40 | Fast | 0.8 | 30 | 3 | 0.33333 | 0.41667 | 0:00 | 12.5 | 60 | 110
|  |  |  | Regular | 0.5 | 10 | 1 | 1 | 2 | 0:10 | 20 | 50
|  |  |  | Boss | 0.3 | 1 | / |  |  | 0:50 |  | /
Initial Gold: 150 |  |  |  | Initial Life: 20
Round | True Interval | Interval (sec) | Interval Begin Time | Name | Speed (grid/sec) | Number | Density (/gird) | gap distance(grid) | gap time (sec) | Spawn Time | Last Time (sec) | Total Gold
1 | 20 | 20 | 0:20 | Fast | 0.8 | 30 | 2 | 0.5 | 0.625 | 0:00 | 18.75 | 60 | 140 | 680
|  |  |  | Fast | 0.8 | 40 | 2 | 0.5 | 0.625 | 0:20 | 25 | 80
2 | 50 | 30 | 0:20 | Regular | 0.5 | 10 | 1 | 1 | 2 | 0:00 | 20 | 50 | 190
|  |  |  | Strong | 0.4 | 10 | 1.5 | 0.66667 | 1.6667 | 0:10 | 16.6667 | 90
|  |  |  | Regular | 0.5 | 10 | 1 | 1 | 2 | 0:30 | 20 | 50
3 | 60 | 40 | 0:30 | Strong | 0.4 | 20 | 0.5 | 2 | 5 | 0:00 | 100 | 180 | 350
|  |  |  | Regular | 0.5 | 10 | 1 | 1 | 2 | 0:20 | 20 | 50
|  |  |  | Regular | 0.5 | 30 | 1 | 1 |  | 0:40 |  | 150
|  |  |  | Boss | 0.3 | 1 | / | /
Initial Gold: 800 |  |  |  | Initial Life: 20
Round | True Interval | Interval (sec) | Interval Begin Time | Name | Speed (grid/sec) | Number | Density (/gird) | gap distance(grid) | gap time (sec) | Spawn Time | Last Time (sec) | Total Gold
1 | 20 | 20 | 0:35 | Regular | 0.5 | 20 | 0.5 | 2 | 4 | 0:00 | 80 | 100 | 325 | 1225
|  |  |  | Regular | 0.5 | 15 | 1 | 1 | 2 |  | 30 | 75
|  |  |  | Regular | 0.5 | 30 | 0.5 | 2 | 4 |  | 120 | 150
2 | 75 | 40 | 0:40 | Fast | 0.8 | 20 | 0.5 | 2 | 2.5 |  | 50 | 40 | 325
|  |  |  | Strong | 0.4 | 10 | 2 | 0.5 | 1.25 |  | 12.5 | 90
|  |  |  | Strong | 0.4 | 15 | 1 | 1 | 2.5 |  | 37.5 | 135
|  |  |  | Fast | 0.8 | 30 | 0.5 | 2 | 2.5 |  | 75 | 60
3 | 90 | 50 | 0:40 | Strong | 0.4 | 10 | 2 | 0.5 | 1.25 |  | 300:00 | 90 | 405
|  |  |  | Strong | 0.4 | 15 | 0.5 | 2 | 5 |  | 75 | 135
|  |  |  | Strong | 0.4 | 20 | 1 | 1 | 2.5 |  | 50 | 180
4 | 80 | 40 | 0:40 | Regular | 0.5 | 10 | 1 | 1 | 2 |  | 20 | 50 | 170
|  |  |  | Fast | 0.8 | 30 | 0.5 | 2 | 2.5 |  | 75 | 60
|  |  |  | Regular | 0.5 | 15 | 2 | 0.5 | 1 |  | 15 | 60
|  |  |  | Boss | 0.3 | 1 | / | /

## Assets Priority
Assets | Art | 3D Assets | Model | Enemies |  | Priority
Regular
Strong
Fast
Boss
|  |  |  | Ball | build
sell
harm
ice
Projectile
bullet for Basic and Double-end
missile
arrow
|  |  | Animation | Enemies Walk
Enemies die
|  | VFX | Tower | Sell
|  |  |  | Build |  | Can be merged
Upgrade
|  |  | projectile | when bullet hit |  | Can be merged
when missile hit
when arrow hit
Enemy
spawn
die
| Sound | SFX | Projectile
when bullet hit
when missile hit
when arrow hit
Ball
|  |  |  | Place |  | Can be merged
Launch
Hit
UI
|  |  |  | Button |  | Can be merged
Lose
Win
BGM
Main Menu
Level

## Feedback
Event/Actions | SFX | VFX | Music | UI | Animation
Enemy Spawn | √
Enemy Die | √
Enemy Enters Base | √
Bullet Hit | √
Missile Hit | √
Crossbow Hit | √
Pull Slingshot | √
Release Slingshot | √
Build Tower | √
Upgrade Tower | √
Sell Tower | √
Successful Purchase | √
No Enough Money/Failed Purchase | √
Boss Spawn | √ |  | √
Boss Die | √
Funtion Menu Switch | √ |  |  | √
System Button | √ |  |  | √
Ice Ball | √ | √
Fire Ball | √ | √
Level Win | √
Level Failure | √

## Ball
Ball Name | Damage | Deceleration Rate | Duration | Range(Radius) | Details
Ice Ball | 0 | 50% | 4s | 1 | Single body attack, no sputtering
Harm Ball | 20 | / | / | 1